## Slide 1
Crop monitoring as an E-agriculture tool in developing countries (E-AGRI)
Summary of the second Periodic Review
FP7 STREP Project (GA 270351)
Final Meeting (2014-01-20)

## Slide 2
E-AGRI 2nd Periodic Review Meeting:
Time and place: April 9, 2013, Brussels
European Commission: Ardiel Cabrera, PO
External Reviewers: Prof. Juergeb Kreyssig (University of Applied Sciences, Braunschweig, GE)
Dr, Nikos VoGIATZIS (Hellenic technology Clusters Initiatives)
Mrs Antal BULANZA, Belgacom
E-AGRI consortium: Qinghan Dong
Allard de Wit
Roberto Confalonieri

## Slide 3
E-AGRI 2nd Periodic Review
Meeting: Commission’s recommendation
1: The progress is acceptable, where the technical advance is good,
while the management effort has been weak (no presentation on UOR).
2. Resubmission of the annual report with more detailed information including roles of task implementing organizations (basically who did what)
3. Resubmission of the deliverables on dissemination activities: D71.3 and D71.5
The three recommendations were integrally followed and the requested report and deliverables were submitted by May 8, 2013. The Commission accepted the submissions on its letter of June10, 2013
The Commission’s recommendations are be summarized:

## Slide 4
E-AGRI 2nd Periodic Review Meeting: Reviewer’s recommendation
Project objective
Focus of reviewers
Management
Aspects of Capacity building
Dissemination activities
Transfer of technology
Reviewers recommendation of the 2nd year | Status
Updated annual report including more detailed information on each of the activities such as implementation bodies and results, as well as information on use of resources (especially from UMIL) | Implemented
Comparative information on the recommendation issued from the 1st review | Implemented
Declaration of a commitment from each of the partners | Not implemented
More elaborated dissemination plan ( new deliverable D71.5) | ??
Involvement by Chinese partners beyond data collection | ??, Implemented

## Slide 5
E-AGRI Project 2nd Periodic Review
Meeting: Reviewer’s recommendation
Reviewers recommendation for final year | Status
Bi-annual report at the 30th month in the same format as annual report | Implemented
PU deliverables made public | ??, Implemented
Updating the project web site | Implemented
More elaborated dissemination plan ( new deliverable D71.5) | ??
Involvement by Chinese partners beyond data collection | ??, Implemented
Dissemination by social media (Twitter, Facebook…) | Not implemented
Quantification of dissemination activities | ??, implemented
More management effort, more man power more time | Not implemented
One self critic from the coordination: too many deliverables (60+) planned and submissions were poorly scheduled

## Slide 6
2nd Periodic Review: Follow-up and actions
User of Resources Table
Dissemination activities including: attended conferences, proceedings, publications, public folders
Trainings, feedback of training
RP3 Report: Before the February 28, 2014: providing an update of the previous Periodic Report, including financial aspects:
Before the February 28, 2014: all deliverables or justification letters
Before the March 15, 2014: Input for the Final report