## Slide 1: WP2 progress
Allard de Wit, Alterra

## Slide 2: WP2: progress Anhui
Limited progress Anhui test site:
  Lack of human resources on Alterra side
  Communication with AIFER colleagues difficult
Prepared and organized CGMS/WOFOST workshop at Hefei (2011/nov/02)
Discussed and renewed list of tasks for Anhui CGMS setup during workshop

## Slide 3: WP2: progress Morocco
Intensive discussion on meteorologic inputs: AURELHY vs Classic CGMS
Basic data sources are available
INRA (Hicham Marzouki) started building CGMS together with Alterra (R. vd Wijngaart)
Riad: How to get operational a.s.a.p. for March 2012 forecast

## Slide 4: CGMS Statistical Toolbox
CGMS Statistical toolbox was developed for Windows XP -> problems under Windows7
Alterra migrated CST to Windows7 recently: fully functional on MS Access database.
Testing on ORACLE (yesterday) revealed some problems to be resolved.

## Slide 5: E-AGRI deliverables: Usability reports Anhui/Morocco
Inventory of available data sources and their suitability for applying CGMS
  Inventory made during Hefei workshop
Inventory of factors explaining regional yield variability in Anhui: irrigation, fertilizer, disease, lodging (hard wind)
  Alterra will create questionaire in January, to be circulated with experts in Anhui/Morocco
Inventory of technical constraints
  e.g. is ORACLE available/usable
  Etc.