## Slide 1
Crop monitoring as an E-agriculture tool in developing countries (E-AGRI)
Summary of the first Periodic Review
FP7 STREP Project (GA 270351)
2nd Progress Meeting (2012-12-10)

## Slide 2
E-AGRI Project 1st Periodic Review
Meeting:
Time and place: May 16 2012, Brussels
European Commission: Ardiel Cabrera, PO
External Reviewers: Dr. Nicolas Chevrollier (BoP Innovation Center, NL)
Prof. Juergeb Kreyssig (University of Applied Sciences, Braunschweig, GE)
Prof. Daoliang Li, (China Agricultural University, CN)
E-AGRI consortium: Qinghan Dong
Allard de Wit
Roberto Confalonieri

## Slide 3
E-AGRI Project 1st Periodic Review:
Agenda:
Presentation on project management
Presentations on WP 2-6
Deliberation
Oral comments from Reviewers
Review Report (2 weeks later)
Recommen-dations from Commission

## Slide 4
E-AGRI Project 1st Periodic Review
Oral Comments from reviewers (email from PO on 16/05/2012)
Activities / WP | Remarks | Comment from the project coordinator (PC)
Management | Non conformity to the EC Periodic Report (PR) model Missing the account of use of resources (UOR) | Knowledge lacking from both PC and (new) PO Resubmission on 31/05/2012
 | A dissemination plan is requested | New deliverable on dissemination agreed
WP2 | Resubmission of D21.3 (Merge of the part A&B) Resubmission of D23.1 New deadline for D22.1 (30/06/2012) New deadline for D22.2 (31/08/2012) New deadline for D23.2 (31/01/2013) | Resubmission agreed for one month after reception of review report
WP3 | Resubmission of D31.1 (Merge of the part A&B) Delay justification letter for approved D32.1 No critics on D34.1 | Agreed for one month after reception of review report
WP4 | D41.1 duplication of D21.3 to be discussed | 
Review Report was expected on 15/06/2012

## Slide 5
E-AGRI Project 1st Periodic Review
Review Report and EC recommendations on 10/08/2013
Activities / WP | Review and recommendations | Corrective action
Management | Delay on deliverable submission is largely pointed Quality of the deliverable Commitment and expertise of partners was questioned Promotional activities have to be enhanced Biannual report Dissemination Plan | While the Consortium privileges the content and quality of work rather the strict administrative schedules, the reviewers considered all these delays as important deviation to work plan. Any delay (deviation) on deliverables should be better managed, using early notice, justification letter, etc.. More attention should be given to the quality of deliverables (language, layout…) Compromise between partners is the best sign of commitment in Commission’s eyes Much promotion during the first two Workshops. Planning 2-3 publications in Morocco and China – Anhui official (agro) journals? New report will be submitted after this meeting. Submitted on 30/08/2012

## Slide 6
E-AGRI Project 1st Periodic Review
Review Report and EC recommendations on 10/08/2013
Activities / WP | Title and recommendations | Action
WP1 | New submission of the Periodic Report (PR) using EC model including “use of resources” (UOR) | Submitted on 2012/05/30 Financial Report (FR) in compliance with UOR submitted on 25/06/2012
WP2: | Re-submission: D21.3 Regional statistic database: merging 2 parts D23.1 Usability Report for CGMS application for Anhui: mitigating missing data, conclusion New deadlines D22.1 Usability Report for CGMS application for Morocco (30/09/2012) D22.2 Strategy report on CGMS adaptation for Morocco (30/10/2012) D23.2 Strategy Report on CGMS adaptation for Anhui (31/12/2012) | Submitted on 23/06/2012 Submitted on 04/07/2012 Submitted on 26/06/2012 Submitted on 21/09/2012

## Slide 7
E-AGRI Project 1st Periodic Review
Review Report and EC recommendations on 10/08/2013
Activities / WP | Deliverables and recommendations | Action
WP3 | Resubmission: D31.1 Ground data collection Report : Merge of the part A&B Delay justification letter: D32.1: Sensitivity Analysis Report Approved: D34.1 Synthetic Report D32.1: Sensitivity Analysis Report | Submitted on 06/07/2012 Sent on 22/06/2012
WP4: | removed: D41.1 Databases on wheat yield for two study regions : duplication of D21.3 | Deleted and the resources are to be discussed
WP7 | New deliverable on dissemination plan, updated for each Periodic Review | Submitted on 30/08/2012

## Slide 8
E-AGRI Project 1st Periodic Review
EC recommendations for the future period
Technical deployment:
Running CGMS at level 2
First yield forecasting using BioMA
Validation of RS indicators at a larger ROI
Starting capacity building in Kenya
Management:
FP7 reporting Knowledge (Period review)
Biannual Reporting
Promotional Work:
Liaise with Government bodies (Local ministries, DG-AGRI)
Attending more specialized symposiums (attended: Dragon, USDA conference, others to be reported?)
Exchange with other teams in the field (visited: Anhui agricultural University (March 2012), China Agriculture University (June 2012); Morocco centre of remote sensing (CRTS); planned: Zhejiang University, Others to be reported?)
Publications: scientific and journalistic (general newspapers?)

## Slide 9
E-AGRI Project 1st Periodic Review
Action list before the next Periodic Review
Biannual Report
User of Resources’ Report
PR Report
List of conferences and symposiums attended and title of presentations or the first page of proceedings
List of the specialized organizations visited and mission summaries
List of publications (scientific and journalistic)

## Slide 10
E-AGRI Project 2nd Periodic Review
Period: The week of XX (18, 25) March or ….1st…….
(combined with a BioMA training session)
Place: Morocco
Experts / Reviewers:
Nikos Vogiatzis
Juergen Kreyssig
Daoliang Li.

## Slide 11
E-AGRI Project 2nd Periodic Review
Sent: Thursday, December 06, 2012 12:44 PM To: Dong Qinghan Subject: E-AGRI project review: not possible on 12-14 March
Dear Dong,
I regret to inform you that due to changes in the evaluation week for the next call of proposals (ICT call 10), it will now take place on the week of 11-15 March.
Therefore, it won't be possible for me to keep the review meeting, workshop and field mission on 12-14 March.
The options I would suggest are either re-scheduling (but I guess this will bring problems for your workshop), or just have a review meeting I Brussels some other day, whenever it suits you best.
I am really sorry about this, but the organisation of the evaluation has just been confirmed to me, and I have little influence in changing it.
Please let me know what you think. Thank you. Best regards,
Ardiel Cabrera Programme Assistant - EU Policies DG CONNECT, Unit D.1 "International"